## Activity Plan Ilham
[20 empty] | APPROVED | [12 empty] | PREPARED
Update Date : March 20rd, 2024 | [31 empty] | Fauzi Muharom
DETAIL ACTIVITY SCHEDULE
NO | ITEMS | ACTIVITY | TARGET | OUTPUT | DUE DATE | PIC | 2024 | [24 empty] | RESULT | REMARK
[7 empty] | AUG |  |  | SEPT |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN |  |  |  | FEB
[7 empty] | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2
I | INTERNSHIP ACTIVITY PROGRAMS
I.1 | COMPANY INDUCTION | Introduction and Profile of PT TMMIN | Knowing what is PT.TMMIN | Contract Signing | August, 6th 2025 | HRD | bar: AUG W2
I.2 | TRAINING
| Safety Dojo | Full day offline training | > Passed the training procedures > 80% minimum passing grade | Training Certificate | August, 7th-8th 2025 | TLC | bar: AUG W2
| Toyota Way | Single-hour Webinar training | bar: AUG W2
| 5R Management | Half-day Offline training | bar: AUG W2
| Basic PDCA | Half-day Webinar training | bar: AUG W2
Basic A3 Report
| JKK Report (TBC) | Offline class training
I.3 | DIVISION ORIENTATION
1. Capability Center Division Introduction
| 1.ACapability Center (Telematics) Induction | Division Induction and group research introductions | Understand Capability Center (Telematics) structures | Capability Center (Telematics) fundamental |  | CCD
| 1.B Understanding Capability Center Purpose and Goal |  | Understand Capability Center (Telematics) Purpose and Goal | Achievement of targets in the capability center | August, 12th 2025 | CCD | bar: AUG W2
| 1.D Know the project planning | Group Discussion | Know the project planning | Power point |  | CCD
| 1.E Plant Tour & xEV Visit | Plan Tour | Get know about manufacturing processes & Electrivication Toyota | Understand About Production Manufacturing Process |  | HRD
I.4 | HR ACTIVITY
| Monthly Sharing with Intern | Hold a meeting with HR | Obtain new knowledge from story of experience during internship at TMMIN | Knowledge and new information |  | HRD
| Toyota Internship Outing | Do outbound outside the work area | Get to know each other between internship participants | Extensive relationships |  | HRD
| Psychotest for selected intern | Psychotest | 100 percent of questions answered | Chance to pass NEDP |  | HRD
| Toyota Internship Graduation Ceremony | Graduation Ceremony | proceed to the NEDP stage | Graduation procession |  | HRD
II | JKK REPORT
II.1 | 1. Identify background of the job | Benchmarking telematics features of several brand | Get to know JKK background | JKK backgound |  | Fauzi
| 2. Identify purpose, target and outputs of the job | Determining the purpose of targets and outputs from JKK that will be taken | Identify The Customer's Ideal State Condition | Final Output with Customer's Ideal State Condition |  | Fauzi
| 2. Develop work process based on the job | Creation of work processes | Develop Process and Breakdown The Work Step | Define Optimal Work Process |  | Fauzi
| 3. Establish developed process | Creating management rules | Establish Management Rules | Define New Management Rules |  | Fauzi
II.2 | JKK Review | Correct the jkk that has been created | The formation of a good and correct JKK | Get Feedback for JKK Report and Presentation |  | Fauzi
III | ASEAN HR VISIT EVENT
III.1
IV | PROJECT ASSIGNMENT
IV.1 | ADAS Project
| 1. Project introduction | Group DiscussionTeams | Division of job desk for each member | Each member works on their own project | 2nd week in August | Fauzi | bar: AUG W2
| 2. Work planning |  | Know the project planning group | Power Point for the project | 2nd week in August | Fauzi | bar: AUG W2
3. Project development
| 3.1 Perencanaan & Analisis Kebutuhan | Mendefinisikan fitur ADAS Lvl 2. Analisis kebutuhan fungsional & non-fungsional. | Tercapainya pemahaman yang jelas dan terukur mengenai ruang lingkup, kapabilitas, batasan sistem, dan kriteria penerimaan oleh pengguna. | Dokumen Spesifikasi Kebutuhan Sistem. Diagram Arsitektur Sistem. Dokumen Skenario Pengujian Penerimaan | August, 14th 2025 | Fauzi | bar: AUG W2
| 3.2 Desain Subsistem Persepsi | Desain arsitektur sensor. Desain algoritma deteksi objek. Desain modul fusi sensor. | Terbentuknya rancangan sistem persepsi yang andal untuk mendeteksi dan mengklasifikasikan objek relevan (kendaraan, marka jalan) di lingkungan sekitar. | Dokumen Desain Subsistem Persepsi. Test case untuk validasi output persepsi. | 3rd week in August | Fauzi | bar: AUG W2
| 3.3 Desain Subsistem Perencanaan | Desain algoritma behavioral planning. Desain algoritma trajectory planning. | Terbentuknya rancangan logika pengambilan keputusan yang aman dan efisien untuk menentukan manuver kendaraan berdasarkan data dari subsistem persepsi. | Dokumen Desain Subsistem Perencanaan. Test case untuk validasi logika keputusan dan lintasan. | 2 weeks in August and September | Fauzi
| 3.4 Desain Subsistem Kontrol | Desain controller untuk aktuator. Desain antarmuka komunikasi dengan kendaraan (CAN Bus). | Terbentuknya rancangan sistem kontrol yang presisi untuk menerjemahkan perintah dari subsistem perencanaan menjadi aksi nyata pada aktuator kendaraan (setir, gas, rem). | Dokumen Desain Subsistem Kontrol. Test case untuk validasi akurasi aktuasi. | 2th week in September | Fauzi
| 3.5 Implementasi & Integrasi Awal | Coding algoritma Persepsi, Perencanaan, Kontrol. Perakitan dan instalasi hardware di kendaraan. | Terwujudnya setiap subsistem dalam bentuk kode yang fungsional dan terpasangnya seluruh komponen perangkat keras pada kendaraan uji coba secara benar dan aman. | Kode sumber untuk setiap subsistem.Prototipe hardware yang terpasang di kendaraan. | 3rd week in September | Fauzi
| 3.6 Pengujian Unit (Unit Testing) | Menguji setiap fungsi secara terisolasi. | Memastikan setiap komponen terkecil dari perangkat lunak (fungsi/kelas) bekerja sesuai spesifikasi desainnya tanpa eror. | Laporan hasil pengujian unit. | 4nd week in September | Fauzi
| 3.7 Pengujian Integrasi Subsistem | Menguji alur data P->P->C. Menguji integrasi software-hardware. | Memastikan semua subsistem (Persepsi, Perencanaan, Kontrol) dapat berkomunikasi dan bekerja sama dengan baik, serta perintah software dapat dieksekusi oleh hardware. | Laporan hasil pengujian integrasi. Subsistem yang terintegrasi dan berfungsi. | October | Fauzi
| 3.8 Pengujian Sistem (System Testing) | Menguji keseluruhan sistem di lingkungan terkontrol. | Memvalidasi bahwa sistem ADAS secara keseluruhan mampu menjalankan fungsi utamanya (mis: mengikuti lajur & kendaraan lain) sesuai spesifikasi dalam skenario yang terkendali. | Laporan hasil pengujian sistem. Sistem ADAS yang fungsional dan terverifikasi. | 1st week in November | Fauzi
| 3.9 Pengujian Penerimaan & Pelaporan | Uji coba di jalan raya. Pengumpulan data dan evaluasi performa. Penyusunan laporan akhir. | Memastikan sistem ADAS bekerja dengan aman dan andal di lingkungan nyata serta memenuhi kriteria penerimaan yang telah ditetapkan di awal proyek. | Laporan hasil pengujian penerimaan. Video demonstrasi sistem. Dokumen Laporan Akhir. | 2st week in November | Fauzi
V | REGULAR JOB
V.1 | Operational Briefing & Daily Activity Reports
| Morning Asakai | briefing about activities to be carried out and reporting what has been done | Feedback from Mentor | Consensus, Points of improvements | Daily | CCD
| Activities Report to Mentor | reporting what has been done | Feedback from Mentor | Consensus, Points of improvements | Daily | CCD
PT. TOYOTA MOTOR MFG INDONESIA
TOYOTA INDONESIA ACADEMY
TOYOTA LEARNING CENTER DEPARTMENT
CCD INTERNSHIP ACTIVITY PLAN
No. Reg
Name
Date of Birth
Address
: 13221035
: Ilham Nalendra Adji
: January,6th 2003
: Karawang, East Java
Major
University
Level Graduation
Graduate
: Electrical Engineering
: Bandung Institute of Technology
: Bachelor Degree
: 2025
PERSONAL DATA
INTERNSHIP TARGET
Gain practical experience in the development and implementation of telematics project in the Capability Center Division.
 Overcome project challenges with the team to improve problem solving and teamwork skills.
 Engage in learning project management, software development, data analysis, and systems integration to expand skills and capabilities.
JKK IMPROVEMENT THEME
DEVELOPMENT OF
TARGET : LAST CUSTOMER & MANAGEMENT

## Activity Plan Prima
[20 empty] | APPROVED | [10 empty] | PREPARED
Update Date : March 20rd, 2024 | [29 empty] | Fauzi Muharom
DETAIL ACTIVITY SCHEDULE
NO | ITEMS | ACTIVITY | TARGET | OUTPUT | DUE DATE | PIC | 2026 | [22 empty] | RESULT | REMARK
[7 empty] | FEB |  |  | MAR |  |  |  | APR |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG
[7 empty] | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
I | INTERNSHIP ACTIVITY PROGRAMS
I.1 | COMPANY INDUCTION | Introduction and Profile of PT TMMIN | Knowing what is PT.TMMIN | Contract Signing | February, 6th 2025 | HRD | bar: FEB W2
I.2 | TRAINING
| Safety Dojo | Full day offline training | > Passed the training procedures > 80% minimum passing grade | Training Certificate | Fevruary, 12th-13th 2025 | TLC | bar: FEB W2
| Toyota Way | Single-hour Webinar training | bar: FEB W2
| 5R Management | Half-day Offline training | bar: FEB W2
| Basic PDCA | Half-day Webinar training | bar: FEB W2
Basic A3 Report
| JKK Report (TBC) | Offline class training
I.3 | DIVISION ORIENTATION
1. Capability Center Division Introduction
| 1.A Capability Center (Telematics) Induction | Division Induction and group research introductions | Understand Capability Center (Telematics) structures | Capability Center (Telematics) fundamental |  | CCD
| 1.B Understanding Capability Center Purpose and Goal |  | Understand Capability Center (Telematics) Purpose and Goal | Achievement of targets in the capability center | February, 6th 2025 | CCD | bar: FEB W2
| 1.D Know the project planning | Group Discussion | Know the project planning | Power point |  | CCD
| 1.E Plant Tour & xEV Visit | Plan Tour | Get know about manufacturing processes & Electrivication Toyota | Understand About Production Manufacturing Process |  | HRD
I.4 | HR ACTIVITY
| Monthly Sharing with Intern | Hold a meeting with HR | Obtain new knowledge from story of experience during internship at TMMIN | Knowledge and new information |  | HRD
| Toyota Internship Outing | Do outbound outside the work area | Get to know each other between internship participants | Extensive relationships |  | HRD
| Psychotest for selected intern | Psychotest | 100 percent of questions answered | Chance to pass NEDP |  | HRD
| Toyota Internship Graduation Ceremony | Graduation Ceremony | proceed to the NEDP stage | Graduation procession |  | HRD
II | JKK REPORT
II.1 | 1. Identify background of the job | Benchmarking telematics features of several brand | Get to know JKK background | JKK backgound |  | Fauzi
| 2. Identify purpose, target and outputs of the job | Determining the purpose of targets and outputs from JKK that will be taken | Identify The Customer's Ideal State Condition | Final Output with Customer's Ideal State Condition |  | Fauzi
| 2. Develop work process based on the job | Creation of work processes | Develop Process and Breakdown The Work Step | Define Optimal Work Process |  | Fauzi
| 3. Establish developed process | Creating management rules | Establish Management Rules | Define New Management Rules |  | Fauzi
II.2 | JKK Review | Correct the jkk that has been created | The formation of a good and correct JKK | Get Feedback for JKK Report and Presentation |  | Fauzi
III | ASEAN HR VISIT EVENT
III.1
IV | PROJECT ASSIGNMENT
IV.1 | ADAS Project
| 1. Project introduction | Group DiscussionTeams | Division of job desk for each member | Each member works on their own project | 2nd week in February | Fauzi | bar: FEB W2
| 2. Work planning |  | Know the project planning group | Power Point for the project | 2nd week in February | Fauzi | bar: FEB W2
3. Project development
| 3.1 Perencanaan & Analisis Kebutuhan | Transfer materi mengenai projek autonomous yang telah dilakukan sebelumnya. (a) membuat logbook dokumentasi sistem lama, (b) mapping sistem existing, possible enrichment, (c) memperlajari lebih lanjut tentang jetson | Tercapainya pemahaman yang jelas dan terukur mengenai ruang lingkup, kapabilitas, batasan sistem, dan sistem yang telah diimplementasikan. | Dokumen spesifikasi Kkebutuhan sistem. Diagram arsitektur sistem. Dokumen sistem yang telah diimplementasikan. | 3rd week in February | Fauzi | bar: FEB W3
| 3.2 Pengujian Sistem Lama dan Desain Subsistem Persepsi | Desain arsitektur subsistem yang terintegrasi CAN Bus. Desain sensor posisi dan algoritma pada steering. Usulan desain transmisi. (a) desain mikrokontroller STM32 terintegrasi CANBus untuk steering, | Terbentuknya rancangan sistem persepsi yang andal, mapping kebutuhan, tantangan, dan urgensi enrichment. | Dokumen desain subsistem persepsi. Trade off analysis solusi sistem. Test case untuk validasi output persepsi. | 4th week in February | Fauzi | bar: FEB W4 to MAR W1
| 3.3 Desain Subsistem Perencanaan Steering Berdasarkan Feedback Sensor Posisi, CAN Bus, dan Transmisi | Desain algoritma kemudi berdasarkan set poin sensor posisi. Desain algoritma closed-loop system berdasarkan. Mapping data CAN Bus pada steering, pedal, dan camera. | Terbentuknya rancangan logika pengambilan kontrol yang aman dan efisien untuk menentukan manuver kendaraan berdasarkan data dari subsistem persepsi. | Dokumen Desain Subsistem Perencanaan. Test case untuk validasi logika keputusan dan lintasan. | 3rd weeks in March | Fauzi | bar: MAR W1 to MAR W2
| 3.4 Desain Subsistem Kontrol Steering berbasis Sensor Posisi, Kontrol Transmisi, dan Manajemen Data CAN Bus | Desain hardware kontrol kemudi, gas, dan apps. Desain pengendali transmisi. Desain antarmuka komunikasi dengan kendaraan (CAN Bus). | Terbentuknya rancangan sistem kontrol yang presisi untuk menerjemahkan perintah dari subsistem perencanaan menjadi aksi nyata pada aktuator kendaraan (setir, gas, rem, dan transmisi). | Dokumen Desain Subsistem Kontrol. Test case untuk validasi akurasi aktuasi. | 4th week in March | Fauzi | bar: MAR W2 to MAR W3; APR W1
| 3.5 Implementasi & Integrasi Awal | Coding algoritma Persepsi, Perencanaan, Kontrol. Perakitan dan instalasi hardware di kendaraan. | Terwujudnya setiap subsistem dalam bentuk kode yang fungsional dan terpasangnya seluruh komponen perangkat keras pada kendaraan uji coba secara benar dan aman. | Kode sumber untuk setiap subsistem. Prototipe hardware yang terpasang di kendaraan. | 3rd week in April | Fauzi | bar: APR W1 to APR W2
| 3.6 Pengujian Unit | Menguji setiap fungsi secara terpisah pada setiap bagian. (a) pengujain kontrol putaran kemudi berdasarkan feedback sudut dan set poin dari Jetson. (b) pengujian CAN Bus untuk throttle, rem, kemudi, dan transmisi | Memastikan setiap komponen terkecil dari perangkat lunak (fungsi/kelas) bekerja sesuai spesifikasi desainnya tanpa eror. | Laporan hasil pengujian unit steering dan transmisi. | 1st week in May | Fauzi | bar: APR W3 to APR W4
| 3.7 Pengujian Integrasi Subsistem | Menguji alur data antar sub sistem. Menguji integrasi software-hardware. Pengujian dilakukan untuk sistem dapat bekerja berdasarkan target yang dikirim dari CAN Bus | Memastikan semua subsistem (Persepsi, Perencanaan, Kontrol) dapat berkomunikasi dan bekerja sama dengan baik, serta perintah software dapat dieksekusi oleh hardware. | Laporan hasil pengujian integrasi. Subsistem yang terintegrasi dan berfungsi. | 3rd week in June | Fauzi | bar: JUN W1 to JUN W2
| 3.8 Pengujian Sistem | Menguji keseluruhan sistem di lingkungan terkontrol. Sistem saling terintegrasi melalui CAN Bus, setiap sektor saling mengirim targe, saling deteksi, dan logging data. | Memvalidasi bahwa sistem ADAS secara keseluruhan mampu menjalankan fungsi utamanya (mis: mengikuti lajur & kendaraan lain) sesuai spesifikasi dalam skenario yang terkendali. | Laporan hasil pengujian sistem. Sistem ADAS yang fungsional dan terverifikasi. | 4th week in June | Fauzi | bar: JUN W2; JUN W4 to JUL W1
| 3.9 Pengujian Penerimaan & Pelaporan | Uji coba di pada mobil. Pengumpulan data dan evaluasi performa. Penyusunan laporan akhir. | Memastikan sistem ADAS bekerja dengan aman dan andal di lingkungan nyata, memastikan setiap sub sistem terintegrasi oleh satu protokol, serta memenuhi kriteria penerimaan yang telah ditetapkan di awal proyek. | Laporan hasil pengujian penerimaan. Video demonstrasi sistem. Dokumen Laporan Akhir. | 4rd week in July | Fauzi | bar: JUL W2 to JUL W4
V | REGULAR JOB
V.1 | Operational Briefing & Daily Activity Reports
| Morning Asakai | briefing about activities to be carried out and reporting what has been done | Feedback from Mentor | Consensus, Points of improvements | Daily | CCD
| Weekly Meeting | Briefing about weekly activities and reporting what have been done among CC division with chief deputy | Feedback from Mentor and Instructions | Consensus, Points of improvements | Weekly | CCD
| Activities Report to Mentor | reporting what has been done | Feedback from Mentor | Consensus, Points of improvements | Daily | CCD
PT. TOYOTA MOTOR MFG INDONESIA
TOYOTA INDONESIA ACADEMY
TOYOTA LEARNING CENTER DEPARTMENT
CCD INTERNSHIP ACTIVITY PLAN
No. Reg
Name
Date of Birth
Address
: 13221035
Prima Nafisman
: Februari,5th 2004
: Karawang, East Java
Major
University
Level Graduation
Graduate
: Electrical Engineering
: Universitas Gadjah Mada
: Bachelor Degree
: 2026
PERSONAL DATA
INTERNSHIP TARGET
Gain practical experience in the development and implementation of telematics project in the Capability Center Division.
 Overcome project challenges with the team to improve problem solving and teamwork skills.
 Engage in learning project management, software development, data analysis, and systems integration to expand skills and capabilities.
JKK IMPROVEMENT THEME
DEVELOPMENT OF
TARGET : LAST CUSTOMER & MANAGEMENT