## General
Plan |  |  |  | Do | Check
Requirement Gathering | #VALUE! | [6 empty] | Acceptence Testing | Action | Pengecekan dilakukan dengan membandingkan desain yang telah dilakukan pada fase plan
| System Analysis | #VALUE! |  |  |  |  | System Testing | #VALUE! |  | Setiap proses check jika sudah oke langsung dibuatkan standardisasi
|  | Software Design | #VALUE! |  |  | Integration Testing | #VALUE!
|  |  | Module Design | #VALUE! | Unit Testing | #VALUE!
|  |  |  | Coding | #VALUE!
Hardware Development

## Specific Horizontal
Plan | [11 empty] | Do |  |  | Check
Requirement Gathering |  |  | #VALUE! | [20 empty] | Acceptence Testing |  |  | Action | Pengecekan dilakukan dengan membandingkan desain yang telah dilakukan pada fase plan
|  |  | System Analysis |  |  | #VALUE! | [14 empty] | System Testing |  |  | #VALUE! |  |  |  | Setiap proses check jika sudah oke langsung dibuatkan standardisasi
[6 empty] | Software Design |  |  | #VALUE! | [8 empty] | Integration Testing |  |  | #VALUE!
[9 empty] | Module Design |  |  | #VALUE! |  |  | Unit Testing |  |  | #VALUE!
[12 empty] | Coding |  |  | #VALUE!
Hardware Development
No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic | No | Topic | Sub Topic

## Specific Vertikal
By Month
V shape | [5 empty] | No | Topic | Sub Topic | 2025 |  |  |  | 2026
[9 empty] | September | October | November | December | January | February
Plan | Requirement Gathering
System Analysis
Software Design
Module Design
Do |  |  |  |  | Coding Hardware Development
Check |  |  |  | Unit Testing
Integration Testing
System Testing
Acceptence Testing
Action

## By Month
By Month
V shape | [5 empty] | No | Sub Topic | 2025 |  |  |  |  | 2026
[8 empty] | August | September | October | November | December | January | February
Plan | Requirement Gathering |  |  |  |  | 1 | Define ADAS Level 2 & 4 goals (e.g., lane keeping or wasd)
[6 empty] | 2 | Identify sensor & hardware requirements
[6 empty] | 3 | Specify integration with Yaris Cross drive-by-wire system
|  | System Analysis |  |  |  | 4 | Analyze system architecture
[6 empty] | 5 | Assess compatibility with ROS framework
|  |  | Software Design |  |  | 6 | Design software modules (path planning, perception)
[6 empty] | 7 | Plan ROS node structure and communication
|  |  |  | Module Design |  | 8 | Design hardware module layout (sensor mounting and wiring)
[6 empty] | 9 | Design microcontroller interface for drive-by wired
Do |  |  |  |  | Coding Hardware Development | 10 | Develop ROS software for sensor data processing
[6 empty] | 11 | Code control algorithms for throttle/steering/braking
[6 empty] | 12 | Assemble and install sensors (camera, radar, lidar)
[6 empty] | 13 | Integrate hardware with Yaris Cross electrical system
Check |  |  |  | Unit Testing |  | 14 | Test individual sensor inputs (e.g., camera detection)
[6 empty] | 15 | Test microcontroller control outputs
|  |  | Integration Testing |  |  | 16 | Test sensor fusion and ROS Integration
[6 empty] | 17 | Validate drivbe-by-wire control response
|  | System Testing |  |  |  | 18 | Conduct end-to-end testing of Level 2 features
[6 empty] | 19 | Simulate Level 4 scenarios (e.g., autonomous navigation)
| Acceptence Testing |  |  |  |  | 20 | Verivy Level 2 functionality in controlled environment
[6 empty] | 21 | Document readiness for future Level 4 scaling
Action

## By Week NEW
PT Toyota Motor Manufacturing Indonesia
Capability Center Division
SOFTWARE ENGINEER GROUP B : Autonomus System
Activity Plan
[11 empty] | Plan Duration | [8 empty] | % Complete
PDCA | V shape |  |  |  |  | No | Sub Topic | 2025 | [24 empty] | 2026
[8 empty] | Aug |  |  |  | September |  |  |  |  | October |  |  |  |  | November | [5 empty] | December |  |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June
[8 empty] | I | II | III | IV | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | VI | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | I | II | III | IV | I | II | III | IV | V | I | II | III | IV | I | II | III | IV
Expertise Exhibition 2026
Plan | Requirement Gathering |  |  |  |  | 1 | Define ADAS Level 2 & 4 goals (e.g., lane keeping or wasd)
[6 empty] | 2 | Identify sensor & H/W requirements
[6 empty] | 3 | Specify integration with Yaris Cross drive-by-wire system
|  | System Analysis |  |  |  | 4 | Analyze system architecture
[6 empty] | 5 | Assess compatibility with ROS framework
|  |  | Software Design |  |  | 6 | Design S/W modules (perception)
[6 empty] | 7 | Design S/W modules (path planning)
[6 empty] | 8 | Design S/W modules (control)
[6 empty] | 9 | Plan ROS node structure and communication
|  |  |  | Module Design |  | 10 | Design H/W module layout (sensor mounting and wiring)
[6 empty] | 11 | Design microcontroller interface for drive-by wired
Do |  |  |  |  | Coding Hardware Development | 12 | Develop ROS S/W for sensor data processing
[6 empty] | 13 | Code control algorithms for throttle/steering/braking
[6 empty] | 14 | Assemble and install sensors (camera, radar, lidar)
[6 empty] | 15 | Integrate H/W with Yaris Cross electrical system
Check |  |  |  | Unit Testing |  | 16 | Test individual sensor inputs (e.g., camera detection)
[6 empty] | 17 | Test microcontroller control outputs
|  |  | Integration Testing |  |  | 18 | Test sensor fusion and ROS Integration
[6 empty] | 19 | Validate drivbe-by-wire control response
|  | System Testing |  |  |  | 20 | Conduct end-to-end testing of Level 2 features
[6 empty] | 21 | Simulate Level 4 scenarios (e.g., autonomous navigation)
| Acceptence Testing |  |  |  |  | 22 | Verify Level 2 functionality in controlled environment
[6 empty] | 23 | Document readiness for future Level 4 scaling
Action
Eid al-Fitr Holiday

## By Week OLD (hidden)
PT Toyota Motor Manufacturing Indonesia
Capability Center Division
SOFTWARE ENGINEER GROUP B : ADAS System Development
[11 empty] | Plan Duration | [5 empty] | % Complete
PDCA | V shape |  |  |  |  | No | Sub Topic | 2025 | [19 empty] | 2026
[8 empty] | 2025-10-01 |  |  |  | 2025-11-01 |  |  |  | 2025-12-01 |  |  |  | 2026-01-01 |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  | 2026-04-01
[8 empty] | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV | I | II | III | IV
Plan | Requirement Gathering |  |  |  |  | 1 | Define ADAS Level 2 & 4 goals (e.g., lane keeping or wasd) | bar: 2025-10-01 I to 2025-10-01 IV
[6 empty] | 2 | Identify sensor & H/W requirements | bar: 2025-10-01 I to 2025-10-01 IV
[6 empty] | 3 | Specify integration with Yaris Cross drive-by-wire system | bar: 2025-10-01 I to 2025-10-01 IV
|  | System Analysis |  |  |  | 4 | Analyze system architecture | bar: 2025-11-01 I to 2025-11-01 II
[6 empty] | 5 | Assess compatibility with ROS framework | bar: 2025-11-01 I to 2025-11-01 II
|  |  | Software Design |  |  | 6 | Design S/W modules (perception) | bar: 2025-11-01 I to 2025-11-01 II
Design S/W modules (path planning) | bar: 2025-11-01 III to 2025-11-01 IV
Design S/W modules (control) | bar: 2025-12-01 I
[6 empty] | 7 | Plan ROS node structure and communication | bar: 2025-12-01 III
|  |  |  | Module Design |  | 8 | Design H/W module layout (sensor mounting and wiring) | bar: 2025-12-01 III
[6 empty] | 9 | Design microcontroller interface for drive-by wired | bar: 2025-12-01 IV to 2026-01-01 I
Do |  |  |  |  | Coding Hardware Development | 10 | Develop ROS S/W for sensor data processing | bar: 2026-01-01 II to 2026-01-01 III
[6 empty] | 11 | Code control algorithms for throttle/steering/braking | bar: 2026-01-01 III
[6 empty] | 12 | Assemble and install sensors (camera, radar, lidar) | bar: 2026-01-01 IV
[6 empty] | 13 | Integrate H/W with Yaris Cross electrical system | bar: 2026-02-01 I to 2026-02-01 II
Check |  |  |  | Unit Testing |  | 14 | Test individual sensor inputs (e.g., camera detection) | bar: 2026-02-01 III to 2026-02-01 IV
[6 empty] | 15 | Test microcontroller control outputs | bar: 2026-03-01 I
|  |  | Integration Testing |  |  | 16 | Test sensor fusion and ROS Integration | bar: 2026-03-01 II to 2026-03-01 III
[6 empty] | 17 | Validate drivbe-by-wire control response | bar: 2026-03-01 II to 2026-03-01 III
|  | System Testing |  |  |  | 18 | Conduct end-to-end testing of Level 2 features | bar: 2026-03-01 II to 2026-03-01 III
[6 empty] | 19 | Simulate Level 4 scenarios (e.g., autonomous navigation) | bar: 2026-03-01 IV
| Acceptence Testing |  |  |  |  | 20 | Verify Level 2 functionality in controlled environment | bar: 2026-04-01 I to 2026-04-01 IV
[6 empty] | 21 | Document readiness for future Level 4 scaling | bar: 2026-04-01 III to 2026-04-01 IV
Action

## Sheet2
2025 | [22 empty] | 2026
Aug |  | September |  |  |  |  | October |  |  |  |  | November | [5 empty] | December |  |  |  |  | January |  |  |  |  | February
IV | V | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV | V | VI | I | II | III | IV | V | I | II | III | IV | V | I | II | III | IV

## By Day
By Day
[9 empty] | Plan Duration | [5 empty] | % Complete
V shape | [5 empty] | No | Sub Topic | [137 empty] | 2026
[23 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February
[8 empty] | IV | [6 empty] | V | [6 empty] | VI | I | [5 empty] | II | [6 empty] | III | [6 empty] | IV | [6 empty] | V |  |  | I |  |  |  | II | [6 empty] | III | [6 empty] | IV | [6 empty] | V | [5 empty] | I | II | [6 empty] | III | [6 empty] | IV | [6 empty] | V | [6 empty] | VI | I | [5 empty] | II | [6 empty] | III | [6 empty] | IV | [6 empty] | V |  |  |  | I |  |  | II | [6 empty] | III | [6 empty] | IV | [6 empty] | V | [6 empty] | I | [6 empty] | II | [6 empty] | III | [6 empty] | IV
[8 empty] | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Plan | Requirement Gathering |  |  |  |  | 1 | Define ADAS Level 2 & 4 goals (e.g., lane keeping or wasd)
[6 empty] | 2 | Identify sensor & hardware requirements
[6 empty] | 3 | Specify integration with Yaris Cross drive-by-wire system
|  | System Analysis |  |  |  | 4 | Analyze system architecture
[6 empty] | 5 | Assess compatibility with ROS framework
|  |  | Software Design |  |  | 6 | Design software modules (path planning, perception)
[6 empty] | 7 | Plan ROS node structure and communication
|  |  |  | Module Design |  | 8 | Design hardware module layout (sensor mounting and wiring)
[6 empty] | 9 | Design microcontroller interface for drive-by wired
Do |  |  |  |  | Coding Hardware Development | 10 | Develop ROS software for sensor data processing
[6 empty] | 11 | Code control algorithms for throttle/steering/braking
[6 empty] | 12 | Assemble and install sensors (camera, radar, lidar)
[6 empty] | 13 | Integrate hardware with Yaris Cross electrical system
Check |  |  |  | Unit Testing |  | 14 | Test individual sensor inputs (e.g., camera detection)
[6 empty] | 15 | Test microcontroller control outputs
|  |  | Integration Testing |  |  | 16 | Test sensor fusion and ROS Integration
[6 empty] | 17 | Validate drivbe-by-wire control response
|  | System Testing |  |  |  | 18 | Conduct end-to-end testing of Level 2 features
[6 empty] | 19 | Simulate Level 4 scenarios (e.g., autonomous navigation)
| Acceptence Testing |  |  |  |  | 20 | Verivy Level 2 functionality in controlled environment
[6 empty] | 21 | Document readiness for future Level 4 scaling
Action